## Summary-GroupIterationProgress
This report has 1 group iteration progress summary sheet to be filled at the end of each iteration by the team leader, 1 project ontribution sheet to be filled by everyone at the end of the semester, and 1 weekly report sheet per student.
This sheet should be completed by the team leader (or other member in the team) by the end of each iteration.
iteration | Date range | accomplishment summary (such as user stories/tasks completed/big progress, good practices used, etc) | Technical issues summary | non-technical issues summary | Process improvement/plan | # of user story points completed | # of user story points in progress | # of issues opened | # of issues closed | # of issues remained | Total work time (h) | Total Individual work time (h) | Total group meeting time (h) | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | # LOC | Test Case Pass Rate | Defect Rate (Defect per KLOC)
0 | 5/10 - 5/15 | 1. Drafted first version of SPPP 2. Completed first version of Risk Management Plan 3. Identified Technology Stack 4. Significant progress drafting requirements 5. Drafted several user stories 6. Stood up JIRA |  |  |  | N/A | N/A | N/A | N/A | N/A | 52.5 | 46.5 | 6 | 16 | 4 | 0.5 | 0 | 0 | 6 | 6 | 14 | N/A | N/A | N/A
1 | 5/16-5/27 | 1. Updated of SPPP Iteration 1 2. Drafted first version SDD Iteration 1 3. Drafted first version STD Iteration 1 5. Implemented user stories (User Registration and Login) Iteration 1 6. Integration of Jira into GitHub | [8 empty] | 63.5 | 61.5 | 2 | 12 | 9 | 15 | 0 | 2 | 4 | 7 | 12.5
2 | 5/27-6/10 |  |  |  |  | 1 | 1 | 64 |  |  | 0
3 | 6/10-6/17 | [9 empty] | 0
Task Types
0 - learning
1 - requirement analysis
2 - design
3 - implementation
4 - test
5 - communication/management
6 - configuration/environment
7 - unclassified

## projectcontribution
This sheet need to be filled by the end of the semester. You should clearly describe your contribution to the group project in each category in the whole semester.
StudentName | SPPP Document | Requirement Analysis on Pivotaltracker | Design Document (SDD) | Testing Documentation (STD) | Presentation | Implementation (code on Github) | Testing (unittest code on Github or manual testing) | Configuration and Deployment | General communication and management | Other Comments
John Gutierrez
Indra Sigicharla
Hongcheng Ding
Uzay Isin Alici
Mengliang Tan
Adriel Domingo
Tyler Gonsalves

## Uzay Isin Alici
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Backup Project Leader, requirement leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | AI tool log(any AI tools used for what tasks, is it helpful? How do you use the results) | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 05/10-05/16 | 7 | 6 | 1 | 0 - learn git and django, read several tutorials 1 - define high level requirements, 5 - make project plan, send reminders to team members 6 - set up git 7 - research similar products, prepare presentation | 3 | 1 |  |  |  | 0.5 | 1 | 0.5 | Use chatgpt to research Django, and elicitate some high level requirements, which we discussed in the team meeting, Use copilot to generate an initial code sketlon, though it requires some manual modification to get it running | 1. Write 3 sections of SPPP 2. Set up git, commit a test message on git 3. Participate in Iteration 0 presentation | 1. not familar with Django framework, hard to write any code on it 2. communication is not clear. Task assignments is not clear. | 1. finish Django tutorial in 2 weeks, be able to create simple Djano hello world project next week 2. Send task assignments to all members again | 0 - continue to learn Django 1 - continue to define requirements 3 - implement a basic hello world on Django | 6
1 | 05/10-05/16 | 6 | 5 | 4 | 0- learn python and django. 6- set up git 7- working on presentation, SPP Risk Management | 3 | [5 empty] | 1 | 4 | N/A | 1. Creating slides for presentation 2. Risk Assesment Excel Sheet | 1. Not familiar with Jira, Django. | 1. Review security requirements for project | 0- Learn Docker and Jira 3- setup Django and Jira | 7
2 | 5/17-5/23 | 10 | 8 | 3 | 0 - learning Docker 1 - Added two user stories 2 - Security and Introduction parts on SDD document 7 - Working on presentation | 1 | 2 | 4 |  |  |  |  | 1 | N/A | 1. SDD Introduction 2. SDD Security Design | No issues | 1. Plan to revise the Security Design section in future SDD iterations based on how implementation progresses, especially around authentication and deployment. | 0- Begin reviewing the frontend/backend flow to align security implementation with the current design. Prepare an early draft of the REST API and outline possible security-related testing scenarios. | 9

## Indra Sigicharla
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Team Leader and Configuration Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | AI tool log(any AI tools used for what tasks, is it helpful? How do you use the results) | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 05/10-05/16 | 10.5 | 5 | 5.5 | 0 - learn django, 1 - define high level requirements, 5 - make project plan, send reminders to team members 6 - set up GitHub repo, setup branch and merges, coordinate with teammates, 7 - prepare presentation, complete SPPP and Risk Management, record video for presentation, release iteration 0 | 2 | 1 | 0 | 0 | 0 | 0.5 | 3.5 | 4.5 | Didn't make use of AI much other than the inbuilt suggestions for code through VSCode while learning Django. | 1. Verified sections of SPPP. 2. Updated Risk Management 3. Set up Git, setup branch and merges 4. Participate in Iteration 0 presentation |  | 1. Start planning for Iteration 1 of the project. | 0 - continue to learn Django 1 - continue to define requirements 3 - Get started on the basic skeleton of the application. | 6
2 | 05/17-05/23 | 0 | 0 | 0
3 | 05/24-05/30 | 0 | 0 | 0
4 | 06/01-06/06 | 0 | 0 | 0
5 | 06/07-06/13 | 0 | 0 | 0
6 | 06/14-06/20 | 0 | 0 | 0

## Adriel Domingo
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Backup Project Leader, requirement leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | AI tool log(any AI tools used for what tasks, is it helpful? How do you use the results) | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 05/10-05/16 | 7 | 6 | 1 | 0 - learn git and django, read several tutorials 1 - define high level requirements, 5 - make project plan, send reminders to team members 6 - set up git 7 - research similar products, prepare presentation | 3 | 1 |  |  |  | 0.5 | 1 | 0.5 | Use chatgpt to research Django, and elicitate some high level requirements, which we discussed in the team meeting, Use copilot to generate an initial code sketlon, though it requires some manual modification to get it running | 1. Write 3 sections of SPPP 2. Set up git, commit a test message on git 3. Participate in Iteration 0 presentation | 1. not familar with Django framework, hard to write any code on it 2. communication is not clear. Task assignments is not clear. | 1. finish Django tutorial in 2 weeks, be able to create simple Djano hello world project next week 2. Send task assignments to all members again | 0 - continue to learn Django 1 - continue to define requirements 3 - implement a basic hello world on Django | 6
1 | 5/10 - 5/15 | 5.5 | 5.5 | 5 | 0 - learn git (lab 1) 5 - set up polls and meeting times, meeting minutes #1 7 - Risk management, SPP document, pressentation slides | 2 |  |  |  |  | 0.5 |  | 3 | n/a | 1. Created some of the deliverable files for team 3 and moved them to team 3 folder 2. Iteration 0 slides 3. Risk management excel sheet | 1. Not familiar with Git | 1. Work on Iteration 1 deliverables | 0 - learn docker 1 - learn and setup Jira | 8
2 | 5/18 - 5/24 | 8 | 8 | 0 | 0 - Jira, docker 1 - Jira 2 - class diagrams 7 - SDD - design patterns, Rest API, three tier architecture | 1 | 1 | 1 |  |  |  |  | 5 | n/a | 1. Updated Jira with user cases 2 . Created UML Diagrams for user cases 3. Design patterns, REST API, and three tier architecture sections of the SDD | 1. Could not attend group meetings due to work conflicts | 1. Able to take more time off. Should be able to attend group meetings moving forward | 0 - learn node.js look at sqlite3 documentation Django Rest Framework
3 | 5/25 - 5/31 |  |  |  | presentation 1, update SPPP
4 | 6/1 - 6/7
5 | 6/8 - 6/14
6 | 6/15 - 6/21

## Hongcheng Ding
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Backup Project Leader, requirement leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | AI tool log(any AI tools used for what tasks, is it helpful? How do you use the results) | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 05/10-05/16 | 7 | 6 | 1 | 0 - learn git and django, read several tutorials 1 - define high level requirements, 5 - make project plan, send reminders to team members 6 - set up git 7 - research similar products, prepare presentation | 3 | 1 |  |  |  | 0.5 | 1 | 0.5 | Use chatgpt to research Django, and elicitate some high level requirements, which we discussed in the team meeting, Use copilot to generate an initial code sketlon, though it requires some manual modification to get it running | 1. Write 3 sections of SPPP 2. Set up git, commit a test message on git 3. Participate in Iteration 0 presentation | 1. not familar with Django framework, hard to write any code on it 2. communication is not clear. Task assignments is not clear. | 1. finish Django tutorial in 2 weeks, be able to create simple Djano hello world project next week 2. Send task assignments to all members again | 0 - continue to learn Django 1 - continue to define requirements 3 - implement a basic hello world on Django | 6
1 | 05/10-05/16 | 6 | 5 | 1 | 0 - learn about git 0 - learn about frontend development 6 - set up git 7 - working on presentation | 2 | [5 empty] | 1 | 0.5 |  | 1. Create slides for presentation | 1. not familar with git | 1. finish Django tutorial in 2 weeks, be able to create simple Djano hello world project next week | 0- Learn Docker and Jira
| 05.18-5/25 | 6 | 5 | 1 | 0 - jira 1- jira 1- add 2 user stories 7 - SDD - RESET api | 1 | 1 | [5 empty] | 3 |  | 1 - SDD class diagram 2 - RESET API section for SDD 3 - Create UML diagram | 1. New to Django, spent extra time learning project structure and URL routing | Reviewed Django documentation and tutorial examples to understand structure. Will continue to build additional endpoints next week. | 0- Create login endpoint，Add JWT authentication，Write test cases | 6

## Mengliang Tan
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: QA Leader Backup Project Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | AI tool log(any AI tools used for what tasks, is it helpful? How do you use the results) | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 05/10-05/16 | 7 | 6 | 1 | 0 - learn git and django, read several tutorials 1 - define high level requirements, 5 - make project plan, send reminders to team members 6 - set up git 7 - research similar products, prepare presentation | 3 | 1 |  |  |  | 0.5 | 1 | 0.5 | Use chatgpt to research Django, and elicitate some high level requirements, which we discussed in the team meeting, Use copilot to generate an initial code sketlon, though it requires some manual modification to get it running | 1. Write 3 sections of SPPP 2. Set up git, commit a test message on git 3. Participate in Iteration 0 presentation | 1. not familar with Django framework, hard to write any code on it 2. communication is not clear. Task assignments is not clear. | 1. finish Django tutorial in 2 weeks, be able to create simple Djano hello world project next week 2. Send task assignments to all members again | 0 - continue to learn Django 1 - continue to define requirements 3 - implement a basic hello world on Django | 6
1 | 05/10-05/16 | 8 | 6 | 5 | 0 - learn about git 0 - learn about backend development using python 5 - minute takers during the meeting 7 - working on presentation | 5 |  |  |  |  | 3.5 |  | 0.5 |  | 1. Taking notes for material discussed during for meeting #3 and #4 2. Creating slides for the presentation | 1. few experience on backend development with django | 1. Will be spending more time looking into tutorials in order to catch up
| 05/18-05/25 | 16 | 13 | 3 | 0 - learn about jira and database design 1 - jira user stories 2 - UML class diagrams 2 - desing databse schema for SDD 5 - taking notes for meetings 7 - write code review process for SPPP | 4 | 1 | 4 |  |  | 3 |  | 1 |  | 1. Taking meetingminutes for group meeting 5, 6, 7 2. Create user stories and UML diagrams for stories 3. desing databse schema for SDD 4. Write code review process for SPPP | 1. No issues | 1. Plan to learn more about backend desing and django

## John Gutierrez
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: All Roles Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | AI tool log(any AI tools used for what tasks, is it helpful? How do you use the results) | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 05/10-05/16 | 7 | 6 | 1 | 0 - learn git and django, read several tutorials 1 - define high level requirements, 5 - make project plan, send reminders to team members 6 - set up git 7 - research similar products, prepare presentation | 3 | 1 |  |  |  | 0.5 | 1 | 0.5 | Use chatgpt to research Django, and elicitate some high level requirements, which we discussed in the team meeting, Use copilot to generate an initial code sketlon, though it requires some manual modification to get it running | 1. Write 3 sections of SPPP 2. Set up git, commit a test message on git 3. Participate in Iteration 0 presentation | 1. not familar with Django framework, hard to write any code on it 2. communication is not clear. Task assignments is not clear. | 1. finish Django tutorial in 2 weeks, be able to create simple Djano hello world project next week 2. Send task assignments to all members again | 0 - continue to learn Django 1 - continue to define requirements 3 - implement a basic hello world on Django | 6
1 | 5/10 - 5/15 | 5 | 5 | 6 | 0 - Learn git and Django, read and watch several tutorials 1 - Work on SPPP file and define high level requirements (essential, Desirable, and Optional) 5 - Help planning meetings and agenda work flow 7 - Research similar products for SPPP file | 2 | 2 |  |  |  | 0.5 |  | 0.5 | Use babani.co to generate mockups included in the SPPP file | 1. Write several sections of SPPP File | No issues during iteration 0 | N/A | 0 - Learn Docker and Jira 1 - Work on user stories and features 3 - Set up project skeleton | 5
2 | 5/17-5/23 | 18 | 12 | 6 | 0 - Learn Jira and its features as well as practice commands 1 - Develop user stories, sub-tasks, and acceptance tests directly involve during iteration 1 deliverable 2 - Develop UML class diagrams for user stories directly involve during iteration 1 deliverable 5 - Send reminders and constantly active in the communication channels 5 - Lead meetings and Team Flow 7 - Update SPPP defect management plan process and build RestAPI presentation 1 | 4 | 4 | 6 |  |  | 1 |  | 1 | N/A | 1. Write sections for SDD iteration 1 2. Update sections for SPPP iteration 1 3. Slide Presentation Video iteration 1. | 1. Communication is not clear 2. Decison making is not clear 3. Assignation of tasks is not clear | 1. Propose a better communication process 2. Propose a better tasks assignment plan | 1. Work on assigned dev tasks 2. Get familiar with automated testing | 10
3 | 5/24-5/30 | 0 | 0
4 | 6/1-6/6 | 0 | 0
5 | 6/7-6/13 | 0 | 0
6 | 6/14-6/20 | 0 | 0

## Tyler Gonsalves
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Configuration Lead, Design and Implementation Team
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | AI tool log(any AI tools used for what tasks, is it helpful? How do you use the results) | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 5/10-5/16 | 8 | 4 | 4 | 6 - Setup Git 6 - Define branching strategy 7 - Created presentation 1 - Review project requirements 5 - Review team roles 2 - Review techonology stack 5 - Drafted progress report |  | 1 | 0.5 |  |  | 1 | 0.5 | 1 | N/A | 1. Created Project Presentation 2. Created Risk Management Template 3. Supported metrics brainstorming 4. Supported git branch strategy selection | 1. Not familiar with django | 1. Review django tutorials | 1. Review django tutorials 2. Write user stories 3. Investigate containerization 4. Support SDD Draft 5. Support STD Draft | 10
2 | 5/17-5/23 | 16.5 | 14.5 | 2 | 6 - Setup Docker containers 2 - Made software architecture diagram and updated SDD 2 - Made software class diagrams and updated SDD 0 - Learning about docker compose 1 - Added two user stories 2 - Identified design patterns to use for project 7 - Migrated Jira issues to Github 4 - Wrote STD | 1 |  | 4 |  | 2 |  | 6 | 1.5 |  | 1. SDD Software Architecture 2. SDD Class Diagrams 3. Project docker containers 4. SDD Design Patterns 5. STD
3 | 5/24-5/30 | 0 | 0
4 | 6/1-6/6 | 0 | 0
5 | 6/7-6/13 | 0 | 0
6 | 6/14-6/20 | 0 | 0