## Sheet1
This sheet provides some common risks in student projects. You should check if it applies to your group project. You should also feel free to add other risks. Exemplary analysis is also added.
Risk Category | Risk Title | Description | Estimated likelihood of occurrence (L: 1-5 with 1 lowest likelihood) | Estimated Impact (I:1-5 with 1 lowest impact) | Estimated retirement Cost (C: 1-5 with 1 lowest cost) | Priority (lowest number has high priority) (6-L)*(6-I)*C) | Responsible engineer | Target completion date | Detailed plan | Execution summary | Status
Personel | Loss team members | One or more team members drop the class | 2 | 4 | 4 | 32 | Team Leader and all members | 2022-06-01 | Redefine the project scope if necessary, and assign the tasks to other team members. | No one dropped the class so far | Open
| add new team members | One or more people join the group | 4 | 3 | 1 | 6 | Team Leader and all members | 2025-05-14 | Assign roles to the new team member and get them updated on all that has happened before. | 1 person got added to our group | closed
| Lack of motivation or responsibility | Members stop contributing to the project | 1 | 5 | 5 | 25 | Team Leader and all members | 2025-06-17 | Team leader must discuss with their teammates about their motivations and responsibility, to make sure that they contribute. If this problem isn't resolved, then the work must be distributed amongst the other teammates. | No lack of motovation so far | open
Communication | duplicate work | multiple members duplicating each others work | 1 | 4 | 4 | 40 | Team Leader and all members | 2025-06-17 | Have regular meetings with all the teammates included in order to have good communication so that tasks are well assigned to each member. | No duplicate work so far | open
| worked on wrong components | member worked on a different task than what was assigned to them | 3 | 5 | 4 | 12 | Team Leader and all members | 2025-06-17 | Redirect the individual to the correct component with updated priorities, and improve the communication between the individual and Team Leader, have regular check-ins about the status of their work. | No wrong work so far. | open
| useless work | member contributes work that is not needed | 1 | 3 | 4 | 60 | Team Leader and all members | 2025-06-17 | Improve the communication between the individual and Team Leader, have regular check-ins about the status of their work. | No useless work so far. | open
| inconsistent work | member's work quality differs week to week | 3 | 5 | 5 | 15 | Team Leader and all members | 2025-06-17 | Improve the communication between the individual and Team Leader, have regular check-ins about the status of their work. | No inconsistent work so far. | open
Requirements | unclear requirements | project requirements are not well defined | 3 | 5 | 5 | 15 | Team Leader and Requirement Leader | 2025-06-17 | Create a list of requirements that each member contributes to, and check back each meeting to work accordingly, and see if they align with the project ideas. | No unclear requirements so far. | open
| scope creep | The project's goals slowly start to go beyond it's original boundaries (out of scope) without checking if they are feasible within the time limits or not. | 4 | 5 | 5 | 10 | Team Leader and Requirement Leader | 2025-06-17 | Define and document the project scope clearly at the start, including detailed requirements and deliverables. | No scope creep so far. | open
| constant requirements changes | project requirements are constantly changing and therefore insiginficant amount of progress is made | 3 | 5 | 5 | 15 | Team Leader and Requirement Leader | 2025-06-17 | Maintain priority for the most important features according to the scope of the project. | No constant requirements changed so far. | open
Management | improper task assignments | member assigned the wrong task to another member | 4 | 5 | 5 | 10 | Team Leader and all members | 2025-06-17 | Assign tasks based on team members' strengths, experience, and skill level, or let the team members pick the tasks that they are more interested in. | No improper tas assignments so far. | open
| improper planning | members did not collaboratively plan future work | 3 | 5 | 5 | 15 | Team Leader and all members | 2025-06-17 | Have proper meetings with the entire team present in order to finalize a plan so that the entire team can effectively contribute to the project, with a clear plan. | No improper tas assignments so far. | open
| lack of management skills | lead members having poor management skills leading to future issues | 2 | 5 | 5 | 20 | Team Leader and all members | 2025-06-17 | Have experienced members to lead the members that have little to no experience in order to learn. | No lack of management skills so far | open
Technology competence | Not familiar with the framework used | member does not know how to correctly implement the framework | 4 | 2 | 2 | 16 | Team Leader and Configuration Leader | 2025-06-17 | Have a teammate who is knowledgeable about the framework help the teammate who is unfamiliar with the framework. | No lack of familiarity so far | open
| Not familiar with the programming language used | member has insufficient programming capabilites with the selected programing language | 4 | 2 | 2 | 16 | Team Leader and Configuration Leader | 2025-06-17 | Provide learning resources to the teammate who is not familiar with the programming language used. | No lack of familiarity so far | open
| Not familiar with unit testing | member does not know how to correctly implement or use unit testing | 4 | 2 | 2 | 16 | Team Leader and Configuration Leader | 2025-06-17 | Review and have learning sessions with the members who are inexperienced in this domain. | No unit testing yet | open
| Other technology incompetence | member is lacking technical skills that are required to complete the project | 4 | 2 | 2 | 16 | Team Leader and Configuration Leader | 2025-06-17 | Provide learning resources to the teammate who might be behind the rest on a case by case basis, so that every member can effectively participate. | No technology used so far. | open
| Not familiar with Git | member does not know how to effectively use Git | 1 | 1 | 1 | 25 | Team Leader and Configuration Leader | 2025-05-14 | Provide Git tutorials and examples so that the teammates that are unfamiliar with it will be able to contribute. | Everyone familiar with git. | closed
Design and implementation | Improper design | the project was not designed properly | 3 | 5 | 5 | 15 | Team Leader and Design and Implementation Leader | 2025-06-17 | Create prototypes in order to figure out the proper final design in order to make the process efficient. | No improper design so far. | open
| improper technology stack | The team chose an incompatable technology stack for their project | 3 | 5 | 5 | 15 | Team Leader and Design and Implementation Leader | 2025-06-17 | Evaluate tech stack based on project needs that were made clear through meetings and proposals. | No technology used so far. | open
| Messy code | Code that does not compy with guidelines such as PEP8. Insufficient commenting | 4 | 5 | 5 | 10 | Team Leader and Design and Implementation Leader | 2025-06-17 | Learn and get familiar with refactoring processes to come up with a better quality of code | No code so far. | open
Testing | Not enough testing | Lots of bugs found in the final implementation of the project | 4 | 5 | 5 | 10 | Team Leader and QA Leader | 2025-06-17 | Complete tests before deployment | No testing yet. | open
Integration and deployment | Not enough time for integration and deployment | The team ran out of time for proper integration and deployment of the project | 5 | 5 | 5 | 5 | Team Leader and all members | 2025-06-17 | Manage the time carefully considering integration and deployment | No integration and deployment yet | open
| Deployment failure | Not enough testing was done such that the project is unable to deploy | 4 | 5 | 5 | 10 | Team Leader and all members | 2025-06-17 | Complete tests before deployment | No deployment failure yet. | open
Security | Data breach | Security was not properly implemented into the project. Unauthorized users are able to access user data | 4 | 5 | 5 | 10 | Team Leader and Security Leader | 2025-06-17 | Find root cause of data breach and fix accordingly | No data breach yet. | open
| Security flaw | Any defect that pertains to the inability to mainatain security within the project | 5 | 5 | 5 | 5 | Team Leader and Security Leader | 2025-06-17 | Find root cause of security flaw and fix accordingly | No security flaw yet. | open
The team member who is adding the new feature should be the one who determines what is correct for the new functionality that was added.
Work together as a team to make sure each developer has the same environment. This is useful so that there aren't accidental bugs added due to environment issues.